BOARD REPORT

AGENDA ITEM:09 
REPORT NUMBER: SLAB/2024/31

| Report to: | The Board |
| --- | --- |
| Meeting date: | 29 July 2024 |
| Report title | Business Plan 2023-24 Progress Report |
| Report category | For Discussion |
| Issue status: | Business as usual |

| Written by: | Andrew McIntosh, Corporate Support Manager |
| --- | --- |
| Director responsible: | Colin Lancaster |
| Presented by: | Andrew McIntosh, Corporate Support Manager |
| Contact details: | mcintoshan@slab.org.uk |

Delivery of Strategic Objectives
Select the Strategic Objective(s) relevant to the issues.

- Our timely, clear, and consistent decisions on legal aid applications and accounts deliver a positive customer experience

- Our client legal services and targeted funding deliver high quality and accessible information, advice, and representation

- We support our people to develop the skills and ways of working needed to deliver our mission, both now and in the future

- Our advice to Ministers supports their decision making on the future of legal aid and SLAB.

Link to Board or Committee remit

The Board has reserved authority to approve SLAB’s annual business plan. The Board considered and approved the 2024-25 business plan in February 2024. The Board is subsequently responsible for overseeing and scrutinising progress against delivery.

Link to Risk Management

The corporate business plan is a key vehicle for us to deliver our Corporate Plan. Our corporate risk register details how we are trying to mitigate against a range of risks that may divert our resources away from delivering this plan of work.

Publication of the paper

We consider this paper suitable for publication.

Previous consideration

| Meeting | Detail |
| --- | --- |
| N/A. | N/A. |

Report

The status of each project is given a traffic light score by the project sponsor. This is based on the risk to the overall delivery of the project and concerns high level issues. For this reason, the status may differ to that which is reported at a project board level which may be dealing with much more granular or very short terms issues. - Green: The project overall is on track in terms of project end date and deliverables. - Amber: Issues exist which might affect the overall success of the project, but these are being dealt with by the project manager and sponsor. Any deviation from the plan remains within tolerance levels. - Red: There are significant risks to the overall success of the project which require corrective action to meet the project’s objectives. The issues cannot be handled solely by the project manager or sponsor. One or more aspects of the project exceed tolerances. The business plan is at an early stage and as such we have no significant concerns regarding our ability to deliver the programme of work. The work to reform the pension scheme has carried over from 2023-24 and whilst this remains amber due to inactivity, this is outside our control and delay to reform does not present significant difficulties for us.

Governance links

| 1. Finance and resources | Delivery of the business plan will need to be delivered within available administrative funding. Availability of resources has the potential to impact on the delivery plans of individual projects. Future restrictions on public funding will impact on the degree of change we can contemplate policy decisions at our hands and maintain good financial management. |
| --- | --- |
| 2. Risk | At a local level, each project within the corporate plan will have its own assessment of risk, with risks escalated as appropriate. This may result in a risk being escalated to the corporate risk register which will be considered by the Audit Committee and the Board. |
| 3. Legal and compliance | We are required by our framework agreement with Scottish Government to have a business plan in place, and published on our website. Progress against the plan will be monitored by the Board and the Scottish Government. |
| 4. Performance | Performance against the plan will be measured through the established business planning update process. Performance on our administration of the schemes will be monitored through our performance benchmarks. A revised set of benchmarks for 2023-24 has been agreed. |
| 5. Equalities impact | Equalities issues are a key driver for much of the activity within the business plan. All activity that results in changes to policies or procedures will be subject to equalities impact assessment. |
| 6. Privacy impact and data protection | N/A. |
| 7. Communications and engagement | We publish the plan itself and we also publish the board papers that deal with progress. |

Conclusion and next steps

The Board is asked to consider progress made in the first quarter of 2024-25 and comment as necessary.

Appendix/further reading

Appendix 1: Business Plan 2024 25 Q1 Update