# Board report

AGENDA ITEM: 		10
REPORT NUMBER: 		SLAB /2025 /27

Report details

Report to:			The Board

Meeting date:		4 August 2025

Report title:			Business Plan Update

Report category:		For discussion

Issue status:			Business as usual

Written by:			Andrew McIntosh, Corporate Support Manager

Director responsible:	Colin Lancaster

Presented by:		Andrew McIntosh

Contact details:		ceo@slab.org.uk

Delivery of Strategic Objectives
Select our relevant Strategic Objective(s).
1 – Administration: Our timely, clear, and consistent decisions on legal aid applications and accounts deliver a positive customer experience.	
2 – Delivery: Our client legal services and targeted funding deliver high quality and accessible information, advice, and representation.
3 – Investing: We support our people to develop the skills and ways of working needed to deliver our mission, both now and in the future.
4 – Shaping: Our insightful, evidence-based and outcome-focused advice to Ministers supports their decision-making on the future of legal aid and SLAB.

Link to Board or Committee remit:	
The Board has reserved authority to approve SLAB’s annual business plan. The Board considered and approved the 2025-26 business plan in March 2025.

The Board is subsequently responsible for overseeing and scrutinising progress against its delivery.

Link to Risk Management:			
The corporate business plan is a key vehicle for us to deliver our Corporate Plan. Our corporate risk register details how we are trying to mitigate against a range of risks that may divert our resources away from delivering this plan of work.

Publication of the paper:			
We consider this paper is suitable for publication.

Previous Consideration 
Meeting: N/A – this is the first progress report against the 2025-26 plan.

# Project status

The status of each project is given a traffic light score by the project sponsor. This is based on the risk to the overall delivery of the project and concerns around high level issues. For this reason, the status may differ to that which is reported at a project board level which may be dealing with more granular or short terms issues. Each score is categorised as follows:

Green: The project overall is on track in terms of project end date and deliverables. Green may also mean that the project has been fully delivered.

This is represented by the symbols 		and 	        .

Amber: Issues or delays exist which may affect the overall success of the project, but these are being dealt with by the project manager and sponsor. Any deviation from the plan remains within tolerance levels and risks to overall delivery are not serious.

This is represented by the symbol             .

Red: There are significant risks to the overall success of the project which require corrective action to meet the project’s objectives. The issues cannot be handled solely by the project manager or sponsor. One or more aspects of the project exceed tolerances.

This is represented by the symbol              .

This report covers the period up to the end of June 2025.

# Progress summary and future reporting

It is early in the business year but there are no serious concerns around our ability to deliver the programme of work at this stage.

We are conscious of comments Members have made when presented with previous updates about trying to ensure the Board has the right balance of information to enable them to assure themselves that progress is being made and key milestones are met without veering into detailed operational matters. We recognise this and will consider what changes could be introduced at the half year’s report.

We also want to ensure that reporting to the Board is well aligned with our new Corporate Planning and Delivery Team and reporting to this group is also a live consideration for us.

### Customer Insight Strategy

A final draft Customer Insight Strategy has been produced and is now out for comment with key staff. A term of reference has also been created for a Customer Insight Steering Group with membership to be confirmed shortly.

Next steps will be for the steering group to agree an implementation plan to be developed and actioned over the remainder of the year. This will encompass a review of current mechanisms for customer feedback and a test and learn of new processes for capturing, collating, and reviewing feedback. This work is focused primarily on generating insight and action to drive improvements in operational service and customer experience, including potential adjustments to business processes. As the work will also inform the identification of operational priorities and development of benchmarks for 2026-27 onwards, as well as feeding into legal aid reform work, we will share the outputs of this work with the Board as it progresses so it can feed into the development of the Corporate Plan.

Solicitor training and support

We currently offer a range of training and resources to solicitors that deliver legal aid services. Support is delivered through a range of formats. The aim is to ensure that we have well-informed solicitors, able to properly advise their clients on legal aid matters, to understand and meet our requirements for applications and accounts and thereby reduce rework, with its associated burdens on themselves and us. Where training is required, we aim to improve the consistency across the organisation in the way that it is delivered, the experience of those trained, the materials that are used and the ways in which we assess the effectiveness of this work.

The first quarter has been spent agreeing the project’s fundamentals such as scope, milestones and project team.

Framework for staff performance management

As reported to the Board previously, we have developed a new staff performance policy. This sets our policy approach to managing staff performance such as how personal objectives should be set.

The policy has been equality impact assessed and staff have been consulted during its development. It will go live on 11 August 2025. We are now beginning work on the guidance to support managers, and the wider framework in which we manage performance.

### Journey to become a trauma informed organisation

In recognition of the increased profile of trauma, the 2024-25 business plan identified the need to research and make recommendations on the development and organisational implications of becoming a trauma informed organisation. A paper has been considered by the Executive Team setting out the current trauma informed landscape, such as Scottish Government’s approach to trauma, current evidence and literature, and the potential implications for public bodies in becoming trauma informed. We are now much clearer on the scope and workstreams to be pursued and will develop these further in the coming weeks.

The Executive Team will undergo training for leaders on trauma during August.

### Corporate Plan 2026-29

The corporate business plan for 2025-26 represents the final year of the 2023-26 Corporate Plan. We will develop the plan for 2026-29 this year in full consultation with the Board.

We have reviewed the organisation’s purpose, mission, and vision with staff and Members. Due to there being no significant change in our role currently, the feedback has been that no significant change is required.

Next steps will be to discuss again with the Board at its strategy session on 1 September, where we can consider possible corporate objectives for the plan. Additional work will be taking place via a project group which will look at complementary aspects of the plan, such as other strategies and plans which will assist with the delivery and a possible refreshment of the organisation’s corporate values.

### Legal Aid Reform – implementation of regulations

We are preparing for implementation of Scottish Government’s package of regulatory changes to be introduced later in the year. We expect there to be four separate sets of regulations – two dealing with the removal of ABWOR (criminal and children’s) and two dealing with revised fees (criminal and AWI).

A full project plan has been developed and agreed jointly with Scottish Government, and their internal process has commenced. The Parliamentary Liaison Unit now has the regulations recorded and will manage and monitor the process. The plan includes consultation but the type of consultation is to be discussed with Scottish Government. We also have draft policy instructions from Scottish Government to comment on.

Whilst we expect the regulations to be introduced to Parliament in December, we are still to agree on an estimated date for coming into force for each set of regulations.

### Legal aid reform – payment review mechanism

The Minister has asked us to provide her with recommendations on how future reviews of legal aid payment arrangements should be approached.

As discussed at the Legal Assistance Policy Committee (LAPC) in June, we have developed some initial advice and shared this with government which we will discuss soon but in the meantime we are reporting this as amber as we do not have a demonstrably achievable plan at this stage as Scottish Government has not had the opportunity to engage fully with the subject matter just yet.

### Legal aid reform – future legal aid

We are working with Scottish Government on development of proposals for future primary legislation, post the May 2026 election.

Year 0 (2025-26) work has been identified and is undergoing detailed planning, again as discussed with the LAPC. This is reported as amber as the period to end of September has been identified as significantly busy with activities on critical path. Any slippage will affect the time available to inform options through evidence from stakeholder consultation.

### Client Legal Services delivery models

This priority extends beyond continuous improvement and applies to CLAO, PDSO and SCL. Key workstreams include a review of the SCL, the piloting and evaluation of hybrid roles across the network, trauma aware training for staff, developing proposals for the use of ‘navigators’, and workforce planning for the network.

This is currently assessed as amber as elements of the work are dependent on further clarity being required around legal aid reform and the need to develop current management capacity in the network.

Governance links

- Finance and resources

Delivery of the business plan will be done within available funding. Availability of resources has the potential to impact on the delivery plans of individual projects. Future restrictions on public funding may impact on the degree of change we can contemplate whilst maintaining good financial management.

- Risk

At a local level, each project within the corporate plan will have its own assessment of risk, with risks escalating as appropriate. This may result in a risk being escalated to the corporate risk register which will be considered by the Audit Committee and the Board.

- Legal and compliance

We are required by our framework agreement with Scottish Government to have a business plan in place and published on our website. Progress against the plan is monitored by the Board and the Scottish Government.

- Performance

Performance against the plan will be measured through the established business planning update process. Performance on our administration of the legal aid schemes will be monitored through our performance benchmarks. A revised set of benchmarks has been agreed.

- Equalities impact

Equalities issues are a key driver for much of the activity within the business plan. All activity that results in changes to policies or procedures will be subject to equalities impact assessment.

- Privacy impact and data protection

N/A.

- Communications and engagement

We publish the plan itself, and we also publish the board papers that deal with progress.

# Conclusion and next steps

The Board is asked to consider progress made on the 2025-26 plan and comment as necessary.

# Appendix and/or further reading links

N/A.